## Sheet1
2021 Cost Table |  |  |  | 2025 Cost Table
Item Name | Cost Date | Cost | Cumulative Cost | Item Name | Cost Date | Cost | Cumulative Cost
Project Start | 2021-02-10 | 0 | 0 | Project Start | 2025-09-03 | 0 | 0
PaintTech EasyDry Paint Booth (Deposit) | 2021-02-27 | 25000 | 25000 | PaintTech EasyDry Paint Booth (Deposit) | 2025-09-15 | 25000 | 25000
Facility Inspection Fees | 2021-02-27 | 1500 | 26500 | Facility Inspection Fees | 2025-09-15 | 1500 | 26500
LADBS Building Permit | 2021-02-27 | 500 | 27000 | LADBS Building Permit | 2025-09-15 | 500 | 27000
LADBS Electrical Permit | 2021-02-27 | 150 | 27150 | LADBS Electrical Permit | 2025-09-15 | 150 | 27150
LADBS Mechanical Permit | 2021-02-27 | 150 | 27300 | LADBS Mechanical Permit | 2025-09-15 | 150 | 27300
LADBS Plumbing Permit | 2021-02-27 | 150 | 27450 | LAFD Sprinkler Permit | 2025-09-15 | 1000 | 28300
LAFD Sprinkler Permit | 2021-02-27 | 1000 | 28450 | SCAQMD Permit to Construct | 2025-09-15 | 1400 | 29700
SCAQMD Permit to Construct | 2021-02-27 | 1400 | 29850 | SCAQMD Permit to Operate | 2025-09-15 | 1200 | 30900
SCAQMD Permit to Operate | 2021-02-27 | 1200 | 31050 | Facility Prep (Electrical, HVAC) Week 1 | 2025-09-15 | 2500 | 33400
Facility Prep (Electrical, HVAC) | 2021-02-27 | 5000 | 36050 | Equipment Rentals (Boom lift, etc.) Week 1 | 2025-09-15 | 665 | 34065
Equipment rentals (Boom lift, etc.) | 2021-02-27 | 1500 | 37550 | Facility Prep (Electrical, HVAC) Week 2 | 2025-09-22 | 2500 | 36565
PaintTech EasyDry Paint Booth (Remaining upon delivery) | 2021-03-28 | 25000 | 62550 | Equipment Rentals (Boom lift, etc.) Week 2 | 2025-09-22 | 665 | 37230
Paint Booth installation | 2021-03-29 | 2000 | 64550 | Equipment Rentals (Boom lift, etc.) Week 3 | 2025-09-27 | 665 | 37895
Sprinkler installation | 2021-04-03 | 5000 | 69550 | PaintTech EasyDry Paint Booth (Remaining upon delivery) | 2025-10-19 | 25000 | 62895
|  |  |  | Paint Booth installation | 2025-10-20 | 4887.1429 | 67782.1429
|  |  |  | Sprinkler Installation | 2025-10-25 | 12217.8571 | 80000
Assumptions:
|  |  |  | 1. Final quote for the new booth installation is: | 80000
2. Assume that 2025 booth is 144% larger than the 2021 installation
|  |  |  | based on the final quote of $80,000. Costs are scaled by: | 144.4%
|  |  |  | 3. Equipment rentals are expected to cost: | 33% | more than last time
4. spread facility prep cost into 2 weeks
5. spread equipment rentals cost into 3 weeks
Formulas:
Cost Date = [Cost Date, row above]