## Sheet1
2025 Cost Table |  |  |  | Comparison Table
Item Name | Cost Date | Cost | Cumulative Cost | Item Name | Cost Date | Planned Cost | Planned Cumulative Cost | Acutal Cost | Acutal Cumulative Cost | Variance
Project Start | 2025-09-03 | 0 | 0 | Project Start | 2025-09-03 | 0 | 0 | 0 | 0 | 0
PaintTech EasyDry Paint Booth (Deposit) | 2025-09-15 | 25000 | 25000 | PaintTech EasyDry Paint Booth (Deposit) | 2025-09-15 | 25000 | 25000 | 25000 | 25000 | 0
Facility Inspection Fees | 2025-09-15 | 1500 | 26500 | Facility Inspection Fees | 2025-09-15 | 1500 | 26500 | 1500 | 26500 | 0
LADBS Building Permit | 2025-09-15 | 500 | 27000 | LADBS Building Permit | 2025-09-15 | 500 | 27000 | 500 | 27000 | 0
LADBS Electrical Permit | 2025-09-15 | 150 | 27150 | LADBS Electrical Permit | 2025-09-15 | 150 | 27150 | 150 | 27150 | 0
LADBS Mechanical Permit | 2025-09-15 | 150 | 27300 | LADBS Mechanical Permit | 2025-09-15 | 150 | 27300 | 150 | 27300 | 0
LAFD Sprinkler Permit | 2025-09-15 | 1000 | 28300 | LAFD Sprinkler Permit | 2025-09-15 | 1000 | 28300 | 1000 | 28300 | 0
SCAQMD Permit to Construct | 2025-09-15 | 1400 | 29700 | SCAQMD Permit to Construct | 2025-09-15 | 1400 | 29700 | 1400 | 29700 | 0
SCAQMD Permit to Operate | 2025-09-15 | 1200 | 30900 | SCAQMD Permit to Operate | 2025-09-15 | 1200 | 30900 | 1200 | 30900 | 0
Facility Prep (Electrical, HVAC) Week 1 | 2025-09-15 | 2500 | 33400 | Facility Prep (Electrical, HVAC) Week 1 | 2025-09-15 | 2500 | 33400 | 2500 | 33400 | 0
Equipment rentals (Boom lift, etc.) Week 1 | 2025-09-15 | 665 | 34065 | Equipment Rentals (Boom lift, etc.) Week 1 | 2025-09-15 | 665 | 34065 | 665 | 34065 | 0
Facility Prep (Electrical, HVAC) Week 2 | 2025-09-22 | 2500 | 36565 | Order Dry Chem System | 2025-09-20 | 0 | 34065 | 8000 | 42065 | 8000
Equipment rentals (Boom lift, etc.) Week 2 | 2025-09-22 | 665 | 37230 | Facility Prep (Electrical, HVAC) Week 2 | 2025-09-22 | 2500 | 36565 | 2500 | 44565 | 8000
Equipment rentals (Boom lift, etc.) Week 3 | 2025-09-27 | 665 | 37895 | Equipment Rentals (Boom lift, etc.) Week 2 | 2025-09-22 | 665 | 37230 | 665 | 45230 | 8000
PaintTech EasyDry Paint Booth (Remaining upon delivery) | 2025-10-19 | 25000 | 62895 | Equipment Rentals (Boom lift, etc.) Week 3 | 2025-09-27 | 665 | 37895 | 665 | 45895 | 8000
Paint Booth installation | 2025-10-20 | 4887.1429 | 67782.1429 | PaintTech EasyDry Paint Booth (Remaining upon delivery) | 2025-10-19 | 25000 | 62895 | 25000 | 70895 | 8000
Sprinkler installation | 2025-10-25 | 12217.8571 | 80000 | Paint Booth installation | 2025-10-20 | 4887.1429 | 67782.1429 | 4887.1429 | 75782.1429 | 8000
|  |  |  | Dry Chem System Installation Labor | 2025-10-25 | 0 | 67782.1429 | 1000 | 76782.1429 | 9000
|  |  |  | Sprinkler installation | 2025-10-25 | 12217.8571 | 80000 | 4218 | 81000.1429 | 1000.1429
Updated 2025 Cost Table
Item Name | Cost Date | Cost | Cumulative Cost
Project Start | 2025-09-03 | 0 | 0
PaintTech EasyDry Paint Booth (Deposit) | 2025-09-15 | 25000 | 25000
Facility Inspection Fees | 2025-09-15 | 1500 | 26500
LADBS Building Permit | 2025-09-15 | 500 | 27000
LADBS Electrical Permit | 2025-09-15 | 150 | 27150
LADBS Mechanical Permit | 2025-09-15 | 150 | 27300
LAFD Sprinkler Permit | 2025-09-15 | 1000 | 28300
SCAQMD Permit to Construct | 2025-09-15 | 1400 | 29700
SCAQMD Permit to Operate | 2025-09-15 | 1200 | 30900
Facility Prep (Electrical, HVAC) Week 1 | 2025-09-15 | 2500 | 33400
Equipment Rentals (Boom lift, etc.) Week 1 | 2025-09-15 | 665 | 34065
Order Dry Chem System | 2025-09-20 | 8000 | 42065
Facility Prep (Electrical, HVAC) Week 2 | 2025-09-22 | 2500 | 44565
Equipment Rentals (Boom lift, etc.) Week 2 | 2025-09-22 | 665 | 45230
Equipment Rentals (Boom lift, etc.) Week 3 | 2025-09-27 | 665 | 45895
PaintTech EasyDry Paint Booth (Remaining upon delivery) | 2025-10-19 | 25000 | 70895
Paint Booth installation | 2025-10-20 | 4887.1429 | 75782.1429
Dry Chem System Installation Labor | 2025-10-25 | 1000 | 76782.1429
Sprinkler installation - Waived, Costs Incurred | 2025-10-25 | 4217.8571 | 81000
Formulas:
Cost Date = [Cost Date, row above]